## Slide 1: Value engineering
Prepared by Lucie Parrot, eng. M.eng, CVS-Life, FSAVE
February 2019

## Slide 2
Value engineering
A methodology aimed at
optimizing the value
of a product, project or process,
existing or under development

## Slide 3
Definition of Value
VALUE =
COST
SATISFACTION OF NEEDS

## Slide 4: Competitiveness
A business is competitive when:
It designs and optimizes its products and puts them on the market quickly and according to clients’ expectations
It manufactures/builds its products efficiently
It manages its business with optimum processes

## Slide 5
Benefits of a team
Knowledge
common
to all
Knowledge
shared by
2 members
Unique
contribution

## Slide 6: Implementation strategy
ADVISED
CLIENT
MARKET
RESEARCH
NEEDS
FUNCTIONAL
ANALYSIS
FUNCTIONAL
PERFORMANCE
SPECIFICATION
CONCEPTUAL
DESIGN
DESIGN TO COST
FMEA
DETAIL
ENGINEERING
CONSTRUCTION
VALUE
ANALYSIS

## Slide 7: Front loading
More work at the beginning of project
Clear and precise specifications, early on
Goal: reduce rework, redesign, rebuild…

## Slide 8: Role of the team members
Each member must bring in his/her expertise in the subject and collaborate during the workshop

## Slide 9
1- Organization phase
2- Information phase
3- Function and cost analysis phase
4- Creativity phase
5- Evaluation phase
6- Development and presentation phase
7- Implementation and follow up phase
The VE Job Plan

## Slide 10
1- Organization phase
State the object of the study and the reasons for it
Define goals and stakes
Define scope and limits
Identify constraints, means, team member and duration

## Slide 11
2- Information phase
Nature of the information:
Technical: reliability, operations, performance, maintenance…
Economical: global costs…
Social: usage, aesthetics, environment, typical client…
legal: safety, guarantees...

## Slide 12
3 – Function analysis
Systematic approach used to express the functions a product must fulfil, in terms of usage and not means, to satisfy the user ’s needs.
AFNOR

## Slide 13: Function analysis
Function analysis is the prime tool to improve the competitiveness of the…
… products a company designs and manufactures
…buildings a group of architects and engineers design and build

## Slide 14: Function analysis
Identify functions: what needs do we have to fulfill? (Verb and noun)
Characterize: performance criteria, levels and flexibility
Organize: what is the logic?
Set into a hierarchy
Analyze costs: cost of functions vs components

## Slide 15: Different uses of each method

## Slide 16: Functional diagram
Mission of
product
Functional group 1
Functional group 2
Functional group 3
Level 1
Level 2
Level 3
function
function
function
function
function
function
function
function
goal
SOLUTIONS
function
function
function

## Slide 18: Estimating functions
Give a value to each function:
cost
Square meters
duration
performance
weight...

## Slide 19: Results of estimation
Distribute the cost objective on the set of functions
Compare the cost of functions
Validate the interest of the client in paying these costs for these functions
Identify the most expensive functions
Identify mismatches between cost and value

## Slide 20: Cost analysis

## Slide 21
Results of cost analysis
Distribute the cost objective on the set of functions
Compare the cost of functions
Validate the interest of the client in paying these costs for these functions
Identify the most expensive functions
identify mismatches between cost and value

## Slide 22: Cost analysis

## Slide 23: Public market
Do commercial activities
Educate population
Attract visitors
Accommodate visitors
Operate market
Ensure health-safety
Encourage social involvement

## Slide 24: Functional performance specification
Document by which a client expresses his needs in terms of service functions and constraints
It is the results of the functional analysis
Afnor NF X 50-150

## Slide 25: Why a FPS?
Describe the needs in a predetermined format
Indicate grey zones
Identify constraints
Give a response template

## Slide 26: Why a FPS?
Let the designer choose freely the best solution
Make the designer responsible for his/her choices
Encourage the client-supplier dialog
Optimize the value of a product
Favour innovation

## Slide 27
4 - Creativity phase
Find the most creative and innovative ways other than the actual ones, to perform the functions
Different methods

## Slide 28
5 - Evaluation phase
Keep ideas which have great potential in helping us achieve our goal
Group remaining ideas in families
Prepare a development plan for remaining ideas

## Slide 29
6 - Development phase
Work on the remaining ideas in order to substantiate the arguments for and against and compare them to the actual situation.

## Slide 30
Development phase
Arguments to present:
feasibility
assumptions
advantages and disadvantages
impacts and risks
investments, savings, cost justification
implementation conditions
etc.

## Slide 31
Building scenarios
If many proposals can be combined
Always build realistic scenarios
Use a theme
Always compare the scenarios to the global actual situation
Prepare a cost/merit graph of scenarios

## Slide 32
Comparing scenarios
Establish comparison criteria and their weight
Evaluate all scenarios and actual situation , on weighted matrix
Evaluate cost of scenarios
Plot cost / merit graph

## Slide 34
Implementation plan
Compatible with the goals and the culture of the company
Calculate implementation efforts
Evaluate risks of recommendations
Propose a leader

## Slide 35
VA / VA Report
Present the results of the workshop, no more no less,
no interpretation from the author,
team report,
clearly recommend a solution,
the client has the last word.

## Slide 36
7- Implementation and follow-up
Implement plan accordingly
Concentrate on solutions accepted by client
Name an internal leader and give him/her authority

## Slide 37: Different VA projects
Optimization of existing products
Traditional use, cost reduction
Examples:
-Frigidaire -Pratt & Whitney
-Thomas & Betts -ABB
- STM

## Slide 38: Different VA projects
New product development:
Expert use, better needs satisfaction, better cost control. Examples:
Bombardier, new snowmobile
Pratt & Whitney, new engine
STM, new train puller
Frigidaire, new stove

## Slide 39: Different VA projects
Process improvements:
Expert use, better needs satisfaction, better cost control, time reduction, error reduction.
Examples:
Rio Tinto, new mining facility
Iron Ore of Canada, new mining facility
RT Alcan, new aluminum process
Xstrata zinc, safer transportation of chemicals

## Slide 40: Different VA projects
Business processes:
Specialized use, reduction of errors, delay or manpower
Examples:
Hydro-Québec: design of office buildings
ABB: process for proposals
RRQ: resource allocation
McGill: engineering student placement

## Slide 41: Different VA projects
Construction projects:
Quebec City Airport, Toronto Airport
Hospitals, health center residence
Bus garage (transit bus, trucks)
New theatres
Refrigerated warehouse
Museums, libraries, public squares
New School of music – McGill
New farmers market
Aquatic centers, sports centers
New intersections

## Slide 42: New insectarium

## Slide 43: New Insectarium
Context: old building not suitable for a growing collection and growing interest from the public, new building and surroundings to be designed, worldwide architecture contest, won by a German group
Value study: reps from the insectarium, architects and engineers, goal: concept was 14% over budget, find ways to reduce cost while fulfilling needs
Results: proposals for over 15% cost reduction and proposals for 1% cost increase, thus budget was achieved with a better project

## Slide 44: Reconstruction of intersection

## Slide 46: Intersection
Context: Proposal from traffic experts did not please stakeholders, 2 years of back and forth, no solution in sight. Project manager suggest a value study to find creative solutions
Study: 25 stakeholders around the table! Back to square 1. Best picture of overall needs with function diagram. Many solutions proposed by group
Results: one solution satisfied all the stakeholders, best balance between needs of all. High cost but problem solved.

## Slide 47: New intersection design

## Slide 48: Value graph of intersection designs

## Slide 49: Jacques-Cartier square

## Slide 50: Jacques-Cartier square
Context: many restaurants have terraces in the summer time, all different styles and location, dismantled every winter. New regulation for location of terrace off the sidewalk, following complaint by wheelchair advocates. The city wanted to be in charge of the terraces.
Study: A proposal from architect was very expensive for the city and refused by the restaurateurs. Goal of value study: find innovative ways to satisfy the city, the users, the restaurateurs
Results: the study showed the life-cycle cost of various options, including a permanent style

## Slide 51: Different types of terrasses
Construction costs
Life cycle costs

## Slide 52: Sports center

## Slide 53: Ice rink

## Slide 54: Ice rink sports complex
Context: developer wanted a specific location for this sports complex, the cost of the structure to accommodate low quality ground was very high, “design-build” team did not want to change design
Study: developer, architect, engineers, came in with half the will to change
Results: a new location was identified and allowed significant cost savings in structure, needs were clearly defined thus project scope was slightly modified

## Slide 55: Museum of modern art

## Slide 56: House of litterature

## Slide 57: Nunavut health center
Context: a health center was designed to be built in 3 locations; after the 1st one built and occupied, nurses started to complain about the many steps in the residence
Workshop: professionals and nurses analyzed the design to improve how it would fulfill the needs, which were not very well captured first
Results: a more flexible construction with much better satisfaction was identified, at the same cost

## Slide 59: Transformation of church

## Slide 60: Outside the church

## Slide 61: Other uses of VA
When competition announces a new menacing product/project
Risk associated to a new product
Significant stakes, monetary or technologically

## Slide 62: Key success factors of VE
Pilot Project choice
Team spirit
Open mind
Use of a moderator
Support for implementation

## Slide 63: Key success factors of VE
Pilot Project choice:
choose a project carefully
do not exaggerate at the beginning
agree on scope
set limits and constraints
define expectations

## Slide 64: Key success factors of VE
Team spirit
full membership
subject matter experts
no boss-employee relations
shared work and benefits

## Slide 65: Key success factors of VE
Open mind:
Accept innovation
Accept all points of view
Do not censor or criticize

## Slide 66: Key success factors of VE
Use a moderator/facilitator:
Train an employee fit for it
Use the services of a specialist
Never wear 2 hats (participant and moderator)
Trust the job plan

## Slide 67: Key success factors of VE
Support implementation:
Give it a chance
Name an internal leader
Give him/her all the required power

## Slide 68: Benefits of VE
Competitive products and services
Better communication
Reduced or controlled costs
More efficient teams
Development of individuals and teams
Better project control

## Slide 69
Conclusion
VE is a tool for competitiveness: satisfaction of needs at the lowest cost
VE can be used for buildings, infrastructures, products, services, processes, etc.
VE can be used at all phases of the life cycle of the “product”, the best being as early as possible

## Slide 70: Project management
Three pillars
time
scope
money
TASK GIVEN
TASK DELIVERED
REDUCE RISK
MAXIMIZE PROFIT
Define
Plan
Execute
Control
Close
Resources

## Slide 71: Project management
Understand the initial requirements
Plan and set feasible and reachable targets
Create a balance between the quality, time, cost, demand and scope
A science and an art of organizing all the components of the project

## Slide 72: How can VE help?
Definition of Value
Value =
Satisfaction of needs
Cost (resources)
SCOPE
MONEY

## Slide 73: Value engineering job plan
Pre WS
What is the goal of the VE session and why?
Workshop
Function and cost analysis
Post WS
Implement best proposals
Follow up
Who will participate?
Creativity and evaluation
Development of Value proposals and presentation
FACILITATED PROCESS

## Slide 74: How VE helps define scope
Function analysis
Identify functions
Organize functions
Characterize functions
Prioritize functions

## Slide 75: Example
Design and construction of a new building:
  The user
  The owner
  Operations
  Maintenance
  End of life

## Slide 76: Example
Danse school
  Receive students (users)
  Minimize noise transmission
  Symbolize movement
  Show progress (parents)
  Accommodate teachers (users)
  Control temperature(operations)
  Ensure security (operations)
  Have access to roof (maintenance)

## Slide 77: Characterizing functions
Function | Criteria | Level | Flex
Receive students | Number of students at a time | 100 | max
Show progress | Occurrence Number of visitors | Once a year 250 | F0 F2
Accommodate teachers | Number of teachers | 6 | F1
Control temperature | Studios Offices | 18 degrees C 20 degrees C | F1 F1
Have access to roof | Type of access | Direct, assisted | F0
Ensure security | Level | Typical school | F0

## Slide 78: Results?
You understand your client’s business better
You know what your project must deliver
You can allocate resources accordingly

## Slide 79: Results?
Now you have scope!

## Slide 80: Let’s go on!
Value =
Satisfaction of needs
Cost (resources)
SCOPE

## Slide 81: Finding the best project
Function analysis
Identify needs
Functions – criteria – level -FLex
Creativity
Find all options (concepts)
Estimate the cost of options
Value graph
Select comparison criteria
Evaluate options = level of satisfaction
Plot on graph: Level of satisfaction/cost

## Slide 82: Value graph
Chart: Cost
| 22
sce 1 | 117
sce 2 | 193
sce 3 | 156
sce 4 | 167

## Slide 83: Now, what else?
Three pillars
time
scope
money
What about time?

## Slide 84: Time savings
Better understanding of wants and needs and nice-to-have
Less back and forth with client
No over design
No under design
Better resource allocation

## Slide 85: Project management
Three pillars
time
scope
money
TASK GIVEN
TASK DELIVERED
REDUCE RISK
MAXIMIZE PROFIT
Define
Plan
Execute
Control
Close